## Product Backlog
Project Name | Amazon
Client | www.amazon.in
Created By | Sheeba Naik
Creation Date | 14.07.23
Approval Date
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Creteria
1 | 005 | Registration Functionality | User should be able to create account if it is not a register user, from "Create your Amazon account" button | Done | 1.User should get error if the user is not a account holder as in the mockup 2.Once user click on create account user should be able to see set of field like username,mobile number,email and password 3.Password should be of minimum length 6 4.Email id should be optional rest all field are mandatory if not field it should give error a per the mockup 5.Country code should be available with the drop-down with the correct code. 6.By default it should take the country code as per the geolocation

## Sprint Planning
Project Name | Amazon.in
Client | www.amazon.in
Created By | Sheeba
Attendees | 1
Creation Date | 14.07.23
Epic | User Story ID | Feature/Title | User Story | Sprint
1 | 005 | Registration Functionality | User should be able to create account if it is not a register user from create your amazon account button | 1
Story Points | Hours
1 | 1 Day
0,1, 1, 2, 3, 5, 8 | Fibinacci series

## Test scenarios
Project- Amazon
User Story ID | 005
Project Name | www.amazon.in
Module Name | Registration functionality
Requirement Number | R005
Test case Type | Functionality Testing
Reference Doccument | N/A
Pre-condition | User should create account
Test Data | http://www.amazon.in
Test Senario number | Description
TS_001 | Non-Account Holder Error Message
TS_002 | Display of Account Creation Fields
TS_003 | Accessible of Account Creation Fields
TS_004 | Minimum Password Length
TS_005 | Mandatory Fields and Error Handling
TS_006 | Country Code Drop-Down
TS_007 | Default Country Code by Geolocation
TS_008 | Display of Consent Message
TS_009 | Successful Creation of Credentials
TS_010 | Successful Login Functionality

## Test cases
Test case number | Test case name | Description | Test Steps | Test Data | Expected Result | Actual Result | Severity | Priority | Tested By | Test Status | Test Creation Date | Test Execution Date
TC_001 | Non-Account Holder Error Message | Verify that an error message is displayed when a non-account holder tries to access the application | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Enter an email ID without being an account holder Step5: Click on Continue | URL: https://www.amazon.in/ Email ID: test123@gmail.com | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Navigate on the sign in page Step4: Should accept the email id without being an account holder Step5: It should display an error message "There was a problem We cannot find an account with that email address" | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Accepted the Email ID without being an account holder Step5: An error message is displayed "There was a problem We cannot find an account with that email address" | High | High | Sheeba | Pass | 14.07.23
TC_002 | Display of Account Creation Fields | Verify that the required fields for creating an account are displayed when the user clicks on " Create your Amazon account " | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button | URL: https://www.amazon.in/ | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible | Medium | High | Sheeba | Pass | 14.07.23
TC_003 | Accessible of Account Creation Fields | Verify that the required fields for creating an account are accessible when the user clicks on " Create your Amazon account " | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button | URL: https://www.amazon.in/ | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible Step7: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible Step7: The fields Your name, Mobile number with Country Code,Email and Password is not accessible | High | High | Sheeba | Fail | 14.07.23
TC_004 | Minimum Password Length | Verify that the password field requires a minimum length of 6 characters. | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Enter Your name Step6: Enter Country Code Step7: Enter Mobile number Step8: Enter Email ID Step9: Enter Password | URL: https://www.amazon.in/ | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: Should accept name and should be visible Step8: Should accept Country code and should be visible Step9: Should accept Mobile and should be visible Step10: Should accept Email ID and should be visible Step11: Should accept password with minimum 6 characters and should be visible | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: Accepted Name and is visible Step8: Accepted the Country code and is visible Step9: Accepted Mobile number and is visible Step10: Accpeted Email ID and is visible Step11: Accepted the password with 6 or more character | Medium | Medium | Sheeba | Pass | 14.07.23
TC_005 | Minimum Password Length | Verify that the password field requires a minimum length of 6 characters. | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Enter Your name Step6: Enter Country Code Step7: Enter Mobile number Step8: Enter Email ID Step9: Enter Password | URL: https://www.amazon.in/ Name: Test Country Code:+91 Mobile number: 123456789 Email: test123@gmail.com Password: 123456 | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: Should accept name and should be visible Step8: Should accept Country code and should be visible Step9: Should accept Mobile and should be visible Step10: Should accept Email ID and should be visible Step11: Should accept password with minimum 6 characters and not visible | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: Accepted Name and is visible Step8: Accepted the Country code and is visible Step9: Accepted Mobile number and is visible Step10: Accpeted Email ID and is visible Step11: Accepted the password with 6 or more characters | Medium | Medium | Sheeba | Pass | 14.07.23
TC_006 | Minimum Password Length | Verify that the password field requires a minimum length of 6 characters. | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Enter Your name Step6: Enter Country Code Step7: Enter Mobile number Step8: Enter Email ID Step9: Enter Password Step10: Click on Continue | URL: https://www.amazon.in/ Name: Test Country Code:+91 Mobile number: 1234567891 Email: test123@gmail.com Password: 1234 | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: Should accept name and should be visible Step8: Should accept Country code and should be visible Step9: Should accept Mobile and should be visible Step10: Should accept Email ID and should be visible Step11: Should accept password with less than 6 characters and should not be visible Step12: Should give an error message "Passwords must be at least 6 characters." | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: Accepted Name and is visible Step8: Accepted the Country code and is visible Step9: Accepted Mobile number and is visible Step10: Accpeted Email ID and is visible Step11: Accepted the password wih less than 6 character Step12: Gives an error message "Passwords must be at least 6 characters." | Medium | Medium | Sheeba | Pass | 14.07.23
TC_007 | Mandatory Fields and Error Handling | Verify all fiels which are mandatory except email field and check whether the appropriate error messages are being displayed when any required field is left empty | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Leave Your name field empty Step6: By default country code is selected as per website Step7: Leave Mobile number field empty Step8: Leave Email ID field empty Step9: Leave Password field empty | URL: https://www.amazon.in/ Name: Empty Country Code:+91 Mobile number: Empty Email: Empty Password: Empty | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: Should not accept empty field and should give an error message of "Enter your name" Step8: Should be seen by default Country code and should be visible Step9: Should not accept empty field and should give an error message of "Enter your mobile number" Step10: Should accept Email ID field empty Step11: Should not accept empty field and should give an error message of "Enter your password" | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: It is not accepting empty field and giving error message "Enter your name" Step8: Country code correct and is visible Step9: It is not accepting empty field and giving error message "Enter your mobile number" Step10: Accpeted Email ID field empty Step11: It is not accepting empty field and giving error message "Enter your password" | High | Medium | Sheeba | Pass | 14.07.23
TC_008 | Mandatory Fields and Error Handling | Verify all fiels which are mandatory except email field and check whether the appropriate error messages are being displayed when any required field is left empty | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Enter Your name Step6: By default country code is selected as per website Step7: Leave Mobile number field empty Step8: Leave Email ID field empty Step9: Leave Password field empty | URL: https://www.amazon.in/ Name: Test Country Code:+91 Mobile number: Empty Email: Empty Password: Empty | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: Should accept name and should be visible Step8: Should be seen by default Country code and should be visible Step9: Should not accept empty field and should give an error message of "Enter your mobile number" after pressing continue button Step10: Should accept Email ID field empty Step11: Should not accept empty field and should give an error message of "Enter your password" after pressing continue button | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: Accepted Name and is visible Step8: Country code correct and is visible Step9: It is not accepting empty field and giving error message "Enter your mobile number" after pressing continue button Step10: Accpeted Email ID field empty Step11: It is not accepting empty field and giving error message "Enter your password" after pressing continue button | High | High | Sheeba | Pass | 14.07.23
TC_009 | Mandatory Fields and Error Handling | Verify all fiels which are mandatory except email field and check whether the appropriate error messages are being displayed when any required field is left empty | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Enter Your name Step6: By default country code is selected as per website Step7: Enter Mobile number Step8: Leave Email ID field empty Step9: Leave Password field empty | URL: https://www.amazon.in/ Name: Test Country Code:+91 Mobile number: 1234567891 Email: Empty Password: Empty | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: Should accept name and should be visible Step8: Should be seen by default Country code and should be visible Step9: Should accept Mobile and should be visible Step10: Should accept Email ID field empty Step11: Should not accept empty field and should give an error message of "Enter your password" after pressing continue button | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: Accepted Name and is visible Step8: Country code correct and is visible Step9: Accepted Mobile number and is visible Step10: Accpeted Email ID field empty Step11: It is not accepting empty field and giving error message "Enter your password" after pressing continue button | High | High | Sheeba | Pass | 14.07.23
TC_010 | Mandatory Fields and Error Handling | Verify all fiels which are mandatory except email field and check whether the appropriate error messages are being displayed when any required field is left empty | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Enter Your name Step6: By default country code is selected as per website Step7: Enter Mobile number Step8: Leave Email ID field empty Step9: Enter Password | URL: https://www.amazon.in/ Name: Test Country Code:+91 Mobile number: 1234567891 Email: test123@gmail.com Password: 123456 | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: Should accept name and should be visible Step8: Should be seen by default Country code and should be visible Step9: Should accept Mobile and should be visible Step10: Should accept Email ID field empty Step11: Should accept password with less than 6 characters and should not be visible | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: Accepted Name and is visible Step8: Country code correct and is visible Step9: Accepted Mobile number and is visible Step10: Accpeted Email ID field empty Step11: Accepted the password and successfully login | High | High | Sheeba | Pass | 14.07.23
TC_011 | Country Code Drop-Down | Verify that the country code is available in a drop-down menu with the correct codes | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Open the country code dropdown menu | URL: https://www.amazon.in/ | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: Select Country code drop-down and verify that all the country codes are correctly listed | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: Country code drop down is selected and list of country code is correctly listed | Low | Low | Sheeba | Pass | 14.07.23
TC_012 | Country Code Drop-Down | Verify that the country code is available in a drop-down menu with the correct codes | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Open the country code dropdown menu | URL: https://www.amazon.in/ | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: Select Country code drop-down and verify that all the country codes are correctly listed | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: Drop down list is not opening | Low | Low | Sheeba | Fail | 14.07.23
TC_013 | Default Country Code by Geolocation | Verify that the country code is automatically populated based on the user's geolocation | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Observe the default country code is automatically populated based on the geolocation | URL: https://www.amazon.in/ | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: The country code field should be pre-filled with the appropriate country code based on the user's geolocation | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: Default country code is displayed correctly based on the user's geolocation | Low | Low | Sheeba | Pass | 14.07.23
TC_014 | Default Country Code by Geolocation | Verify that the country code is automatically populated based on the user's geolocation | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Observe the default country code is automatically populated based on the geolocation | URL: https://www.amazon.in/ | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: The country code field should be pre-filled with the appropriate country code based on the user's geolocation | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: The default country code is not populated based on the geolocation | Low | Low | Sheeba | Fail | 14.07.23
TC_015 | Default Country Code by Geolocation | Verify that the country code is automatically populated based on the user's geolocation | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Observe the default country code is automatically populated based on the geolocation | URL: https://www.amazon.in/ | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: The country code field should be pre-filled with the appropriate country code based on the user's geolocation | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: The default country code is incorrect based on the geolocation | Low | Low | Sheeba | Fail | 14.07.23
TC_016 | Default Country Code by Geolocation | Verify that the country code is automatically populated based on the user's geolocation | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Observe the default country code is automatically populated based on the geolocation Step6: Change the Country code Step7: Click on continue button | URL: https://www.amazon.in/ | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: The country code field should be pre-filled with the appropriate country code based on the user's geolocation Step8: Should accept the changed country code Step9: Should give an error message "There was a problem Please enter a valid mobile phone number with area code." | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: Default country code is displayed correctly based on the user's geolocation Step8: Accepted the changed country code Step9: Registration fails and gives an error message of "There was a problem Please enter a valid mobile phone number with area code." | Medium | Medium | Sheeba | Pass | 14.07.23
TC_017 | Default Country Code by Geolocation | Verify that the country code is automatically populated based on the user's geolocation | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Observe the default country code is automatically populated based on the geolocation Step6: Change the Country code Step7: Click on continue button | URL: https://www.amazon.in/ | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: The country code field should be pre-filled with the appropriate country code based on the user's geolocation Step8: Should accept the changed country code Step9: It should not accept the changed country code and give an error message "There was a problem Please enter a valid mobile phone number with area code." | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: Default country code is displayed correctly based on the user's geolocation Step8: Accepted the changed country code Step9: It is accepting the wrong country code and the user is registered with no error message | High | High | Sheeba | Fail | 14.07.23
TC_018 | Display of Consent Message | Ensure that the message regarding consent to receive security notifications is displayed on the screen | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Verify the consent message | URL: https://www.amazon.in/ | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: The message "By enrolling your mobile phone number, you consent to receive automated security notifications via text message from Amazon. Message and data rates may apply" should be visible on the screen | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: The message "By enrolling your mobile phone number, you consent to receive automated security notifications via text message from Amazon. Message and data rates may apply" is visible on the screen | Low | Low | Sheeba | Pass | 14.07.23
TC_019 | Display of Consent Message | Ensure that the message regarding consent to receive security notifications is displayed on the screen | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Verify the consent message | URL: https://www.amazon.in/ | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: The message "By enrolling your mobile phone number, you consent to receive automated security notifications via text message from Amazon. Message and data rates may apply" should be visible on the screen | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: The message "By enrolling your mobile phone number, you consent to receive automated security notifications via text message from Amazon. Message and data rates may apply" is not visible on the screen | Low | Low | Sheeba | Fail | 14.07.23
TC_020 | Successful Creation of Credentials | Verify that the user can successfully create credential | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Enter Your name Step6: By default country code is selected as per website Step7: Enter Mobile number Step8: Leave Email ID field empty Step9: Enter Password Step10: Solve puzzle to protect your account | URL: https://www.amazon.in/ Name: Test Country Code:+91 Mobile number: 1234567891 Email: test123@gmail.com Password: 123456 | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: Should accept name and should be visible Step8: Should be seen by default Country code and should be visible Step9: Should accept Mobile and should be visible Step10: Should accept Email ID field empty Step11: Should accept password with less than 6 characters and should not be visible Step12: Should solve the puzzle to protect your account Step13:User should be redirected to the login page with a success message indicating that the account has been created | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: Accepted Name and is visible Step8: Country code correct and is visible Step9: Accepted Mobile number and is visible Step10: Accpeted Email ID field empty Step11: Accepted the password Step12: Solved the puzzle and created successful creadentials for login Step13: User is redirected to the login page with a success message indicating that the account has been created | High | High | Sheeba | Pass | 14.07.23
TC_021 | Successful Login Functionality | Verify that the user can successfully log in with the created credentials | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Enter Email or mobile phone number Step5: Click on Continue Step6: Enter password Step7: Click on Continue | URL: https://www.amazon.in/ Mobile number: 1234567891 Email: test123@gmail.com Password: 123456 | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should accept the Email or mobile phone number and it should be visible Step5: Should navigate to the password page Step6: Should accept the password Step7: The user should be able to log in successfully and navigate to the amazon home page with your name on homepage | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Accepted the Email or mobile phone number and is visible Step5: Navigated to the password page Step6: Accepted the password and is visible Step7: The user is able to log in successfully and landed on the amazon home page with your name on the homepage | High | High | Sheeba | Pass | 14.07.23
TC_022 | Successful Creation of Credentials | Verify that the user cannot enter wrong Email ID | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Enter Your name Step6: By default country code is selected as per geolocation Step7: Enter Mobile number Step8: Enter Email Id Step9: Enter Password Step10: Click on continue button | URL: https://www.amazon.in/ Mobile number: 1234567891 Email: test123@gmail Password: 123456 | Step1: Should land on the amazon application dashboard Step2: Sign in drop-drown should be visible Step3: Should navigate on the sign in page Step4: Should be able to click on "Create your Amazon account" button and should be visble Step5: Should navigate to Create account page Step6: The fields Your name, Mobile number with Country Code,Email and Password should be visible and accessible Step7: Should accept name and should be visible Step8: Should be seen by default Country code and should be visible Step9: Should accept Mobile and should be visible Step10: Should accept Email ID Step11: Should accept password with 6 characters and should not be visible Step12: Continue button should get clicked and should be visible | Step1: Landed on the amazon application dashboard Step2: Drop-down is visible Step3: Landed on the Sign in page Step4: Able to click on "Create your Amazon account" button and is visible Step5: Landed on registration page Step6: The fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step7: Accepted Name and is visible Step8: Country code correct and is visible Step9: Accepted Mobile number and is visible Step10: Accepted the Email ID Step11: Accepted the password Step12: Registration fails and gives an error message of " Enter a valid email address" | Low | Low | Sheeba | Pass | 26.07.23 | 26.07.23

## Test excution details
User Story 005
Test case number | Test case name | Description | Screenshot
TC_001 | Non-Account Holder Error Message | Verify that an error message is displayed when a non-account holder tries to access the application
TC_002 | Display of Account Creation Fields | Verify that the required fields for creating an account are displayed when the user clicks on " Create your Amazon account "
TC_004 | Minimum Password Length | Verify that the password field requires a minimum length of 6 characters.
TC_007 | Mandatory Fields and Error Handling | Verify all fiels which are mandatory except email field and check whether the appropriate error messages are being displayed when any required field is left empty
TC_011 | Country Code Drop-Down | Verify that the country code is available in a drop-down menu with the correct codes
TC_013 | Default Country Code by Geolocation | Verify that the country code is automatically populated based on the user's geolocation
TC_018 | Display of Consent Message | Ensure that the message regarding consent to receive security notifications is displayed on the screen
TC_020 | Successful Creation of Credentials | Verify that the user can successfully create credential
TC_021 | Successful Login Functionality | Verify that the user can successfully log in with the created credentials
TC_022 | Successful Creation of Credentials | Verify that the user cannot enter wrong Email ID

## Defects
Defect number | Project Name | Module Name | Requirement Number | Test Case ID | Summary | Description | Issues | Severity | Priority | Assign to
DF_001 | Amazon | Registration Functionality | R005 | TC_003 | Accessible of Account Creation Fields | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Landed on new page and the fields Your name, Mobile number with Country Code,Email and Password is visible Step6: The fields Your name, Mobile number with Country Code,Email and Password is not accessible | The fields Your name, Mobile number with Country Code,Email and Password is not accessible | High | High | Sheeba
DF_002 | Amazon | Registration Functionality | R005 | TC_012 | Country Code Drop-Down | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Landed on new page and the fields Your name, Mobile number with Country Code,Email and Password is visible and accessible Step6: Drop down list is not opening | Unable to select country code and drop down list is not opening | Low | Low | Sheeba
DF_003 | Amazon | Registration Functionality | R005 | TC_014 | Default Country Code by Geolocation | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Landed on new page and observe the default country code is not populated based on the geolocation | The default country code is not populated based on the geolocation | Low | Low | Sheeba
DF_004 | Amazon | Registration Functionality | R005 | TC_015 | Default Country Code by Geolocation | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Landed on new page and observe the default country code is incorrect based on the geolocation | The default country code is incorrect based on the geolocation | Low | Low | Sheeba
DF_005 | Amazon | Registration Functionality | R005 | TC_017 | Default Country Code by Geolocation | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Landed on new page and observe the default country code is automatically populated based on the geolocation Step6: Change the Country code Step7: It is accepting the wrong country code Step8: Click on continue button and the user is registered with no error message | It is accepting the wrong country code and the user is registered with no error message | High | High | Sheeba
DF_006 | Amazon | Registration Functionality | R005 | TC_019 | Display of Consent Message | Step1: Launch the amazon application url Step2: Locate and point out the sign in Step3: Click on sign in button Step4: Click on Create your Amazon account button Step5: Landed on new page and observe and the consent message is not visible on the screen | The message "By enrolling your mobile phone number, you consent to receive automated security notifications via text message from Amazon. Message and data rates may apply" is not visible on the screen | Medium | Medium | Sheeba

## Defect_Snapshots
User Story 005
Defect number | Issues
DF_001 | The fields Your name, Mobile number with Country Code,Email and Password is not accessible
DF_002 | Unable to select country code and drop down list is not opening
DF_003 | The default country code is not populated based on the geolocation
DF_004 | The default country code is incorrect based on the geolocation
DF_005 | It is accepting the wrong country code and the user is registered with no error message
DF_006 | The message "By enrolling your mobile phone number, you consent to receive automated security notifications via text message from Amazon. Message and data rates may apply" is not visible on the screen

## Story_Point_Effort_and_Reason
Project Name :- | Amazon
Story Point :- | 2
Reason for story point :- | In order to write all the test cases we have to check the registration form thorougly which should include checking all the aspects of the form like front end validation,behaviour etc.
Efforts(in hours) :- | 16
Reason for Efforts :- | 4-Creation of test cases 4-Execution of test cases 2-Defect/Bug raising 2-Re-testing 4-Documentation

## Test report
SNO | PASS | FAIL | BLOCKERS | NOT EXECUTED | TOTAL TEST CASE | PASS RATIO (%) | TEST IN PROGRESS | DEV IN PROGRESS | DONE | TOTAL DEFECT
1 | 16 | 6 | 0 | 0 | 22 | 72.73% | 0 | 0 | Y | 6