## Product Backlog
Project Name | Freshworks
Client | https://www.freshworks.com/
Created By | Sheeba Naik
Creation Date | 31.08.23
Approval Date
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Creteria
1 | 002 | Quotes Functionality | User should be able to upload the Quotes and Multi and Single Quotes selection | Done | 1.User should be able to see Quotes Tab with My Quotes 2.User should be able to see the existing Quotes 3.User should be to select Multiple Quotes all Together 4.User should be able to see edit account on the grid 5.All the Columns are Sortable

## Sprint Planning
Project Name | Freshworks
Client | https://www.freshworks.com/
Created By | Sheeba
Attendees | 1
Creation Date | 31.07.23
Epic | User Story ID | Feature/Title | User Story | Sprint
1 | 002 | Quotes Functionality | User should be able to upload the Quotes and Multi and Single Quotes selection | 1
Story Points | Hours
1 | 1 Day
0,1, 1, 2, 3, 5, 8 | Fibinacci series

## Test scenarios
Project-
User Story ID | 002
Project Name | Fresh Sales
Module Name | Quotes functionality
Requirement Number | R002
Test case Type | Functionality Testing
Reference Document | NA
Pre-condition | NA
Test Data | https://www.freshworks.com/
Test Senario number | Description
TS_001 | Quotes Tab with My Quotes
TS_002 | View Existing Quotes
TS_003 | Select Multiple Quotes Together
TS_004 | Edit Account on the Grid
TS_005 | Sortable Columns

## Test cases
Test case number | Test case name | Description | Test Steps | Test Data | Expected Result | Actual Result | Severity | Priority | Tested By | Test Status | Test Creation Date | Test Execution Date
TC_001 | Quotes Tab with My Quotes | First time user- Verify the presence of the Quotes tab with My Quotes using "Got it" button | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on next button of tool tip Step10: New tool tip got popped-up and click on the Got it button | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page Step9: Tool tip should be visible and accessible with its next button option and close icon Step10: New tool tip should be visible & accessible. Also, it should get closed Step11: The Dashboard should display Quotes Tab with the option "My Quotes" and should be visible | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page Step9: Tool tip is visible and and accessible with its next button option and close icon Step10: New tool tip is visible & accessible. Also, it got closed Step11: The Dashboard displayed Quotes Tab with the option "My Quotes" and is visible | Low | Medium | Sheeba | Pass | 31.07.23 | 01.08.23
TC_002 | Quotes Tab with My Quotes | First time user- Verify the presence of the Quotes tab with My Quotes using "close" button | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on close icon of tool tip Step10: New tool tip got popped-up and click on the close icon Step11: | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page Step9: Tool tip should be visible and accessible with its next button option and close icon Step10: New tool tip should be visible & accessible. Also, it should get closed Step11: The Dashboard should display Quotes Tab with the option "My Quotes" and should be visible | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page Step9: Tool tip is visible and and accessible with its next button option and close icon Step10: New tool tip is visible & accessible. Also, it got closed Step11: The Dashboard displayed Quotes Tab with the option "My Quotes" and is visible | Low | Medium | Sheeba | Pass | 31.07.23 | 01.08.23
TC_003 | Quotes Tab with My Quotes | Regular user- Verify the presence of the Quotes tab with My Quotes | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and icon should be selected of Deal Management Step9: The Dashboard should display Quotes Tab with the option "My Quotes" and should be visible | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and icon is selected of Deal Management Step9: The Dashboard displayed Quotes Tab with the option "My Quotes" and is visible | Low | Medium | Sheeba | Pass | 31.07.23 | 01.08.23
TC_004 | Quotes Tab with My Quotes | Verify the presence of the Quotes tab with My Quotes | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and icon should be selected of Deal Management Step9: The Dashboard should display Quotes Tab with the option "My Quotes" and should be visible | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and icon is selected of Deal Management Step9: The Dashboard displayed Quotes Tab without the option "My Quotes" and is not visible | Low | Medium | Sheeba | Fail | 31.07.23 | 01.08.23
TC_005 | View Existing Quotes | Verify the visibility of existing Quotes | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page Step9: The existing Quotes should be visible on the page | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page Step9: The existing Quotes is visible on the page | High | High | Sheeba | Pass | 31.07.23 | 01.08.23
TC_006 | View Existing Quotes | Verify the visibility of existing Quotes | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page Step9: The existing Quotes should be visible on the page | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page Step9: The existing Quotes is not visible on the page | High | High | Sheeba | Fail | 31.07.23 | 01.08.23
TC_007 | Select Multiple Quotes Together | Verify the ability to select multiple Quotes simultaneously | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Select the multiple quotes using checkbox | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and existing Quotes should be visible Step9: Should able to select multiple quotes at once using checkbox | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and existing Quotes is visible Step9: Able to select multiple quotes at once using checkbox | Medium | High | Sheeba | Pass | 31.07.23 | 01.08.23
TC_008 | Select Multiple Quotes Together | Verify the ability to select multiple Quotes one by one | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Select the multiple quotes using checkbox | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and existing Quotes should be visible Step9: Should able to select multiple quotes one by one using checkboxes | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and existing Quotes is visible Step9: Able to select multiple quotes one by one using checkboxes | Medium | High | Sheeba | Pass | 31.07.23 | 01.08.23
TC_009 | Select Multiple Quotes Together | Verify the ability to select multiple Quotes simultaneously | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Select the multiple quotes using checkbox | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and existing Quotes should be visible Step9: Should able to select multiple quotes one by one using checkboxes | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and existing Quotes is visible Step9: Not able to select multiple quotes one by one using checkboxes | Medium | High | Sheeba | Fail | 31.07.23 | 01.08.23
TC_010 | Edit Account on the Grid | Verify the visibility of the "Edit Account" option on the grid view of "Quote name" column | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on the edit option of each quotes present on the grid view of "Quote name" column | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and existing Quotes should be visible Step9: The "Edit Account" option should be visible and accessible on the grid view for each Quote of "Quote name" column | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and existing Quotes is visible Step9: The "Edit Account" option is visible and accessible on the grid view for each Quote of "Quote name" column | Medium | Medium | Sheeba | Pass | 31.07.23 | 01.08.23
TC_011 | Edit Account on the Grid | Verify the visibility of the "Edit Account" option on grid on the grid view of "Quote name" column | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on the edit option of each quotes present on the grid view of "Quote name" column | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and existing Quotes should be visible Step9: The "Edit Account" option should be visible and accessible on the grid view for each Quote of "Quote name" column | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and existing Quotes is visible Step9: The "Edit Account" option is visible but not accessible on the grid view for each Quote of "Quote name" column | High | High | Sheeba | Fail | 31.07.23 | 01.08.23
TC_012 | Edit Account on the Grid | Verify the visibility of the "Edit Account" option on the grid view of "Primary Contact" column | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on the edit option of each quotes present on the grid view of "Primary Contact" column | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and existing Quotes should be visible Step9: The "Edit Account" option should be visible and accessible on the grid view for each Quote of "Primary Contact" column | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and existing Quotes is visible Step9: The "Edit Account" option is visible and accessible on the grid view for each Quote of "Primary Contact" column | High | High | Sheeba | Pass | 31.07.23 | 01.08.23
TC_013 | Edit Account on the Grid | Verify the visibility of the "Edit Account" option on the grid view of "Quote Stage" column | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on the edit option of each quotes present on the grid view of "Quote Stage" column | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and existing Quotes should be visible Step9: The "Edit Account" option should be visible and accessible on the grid view for each Quote of "Quote Stage" column | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and existing Quotes is visible Step9: The "Edit Account" option is visible and accessible on the grid view for each Quote of "Quote Stage" column | High | High | Sheeba | Pass | 31.07.23 | 01.08.23
TC_014 | Edit Account on the Grid | Verify the visibility of the "Edit Account" option on the grid view of "Created at" column | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on the edit option of each quotes present on the grid view of "Created at" column | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and existing Quotes should be visible Step9: The "Edit Account" option should be visible and accessible on the grid view for each Quote of "Created at" column | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and existing Quotes is visible Step9: The "Edit Account" option is visible and accessible on the grid view for each Quote of "Created at" column | High | High | Sheeba | Pass | 31.07.23 | 01.08.23
TC_015 | Sortable Columns | Verify the sorting functionality of "Quote Name" column | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on a column header of "Quote name" to sort data | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and existing Quotes should be visible Step9: Quote name column in the grid view should be sortable and after clicking it should sort the data in ascending order or descending order | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and existing Quotes is visible Step9: Quote name column in the grid view is sortable and after clicking it is sorting the data in ascending or descending order | Medium | High | Sheeba | Pass | 31.07.23 | 01.08.23
TC_016 | Sortable Columns | Verify the sorting functionality of "Quote Stage" column | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on a column header of "Quote Stage" to sort data | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and existing Quotes should be visible Step9: Quote Stage column in the grid view should be sortable and after clicking it should sort the data in ascending order or descending order | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and existing Quotes is visible Step9: Quote Stage column in the grid view is sortable and after clicking it is sorting the data in ascending or descending order | Medium | High | Sheeba | Pass | 31.07.23 | 01.08.23
TC_017 | Sortable Columns | Verify the sorting functionality of "Created at" column | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on a column header of "Created at" to sort data | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and existing Quotes should be visible Step9: Created at column in the grid view should be sortable and after clicking it should sort the data in ascending order or descending order | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and existing Quotes is visible Step9: Created at column in the grid view is sortable and after clicking it is sorting the data in ascending or descending order | Medium | High | Sheeba | Pass | 31.07.23 | 01.08.23
TC_018 | Sortable Columns | Verify the sorting functionality of "Created at" column | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on a column header of "Created at" to sort data | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and existing Quotes should be visible Step9: Created at column in the grid view should be sortable and after clicking it should sort the data in ascending order or descending order | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and existing Quotes is visible Step9: Created at column in the grid view is sortable and after clicking it is not sorting the data in ascending or descending order | Medium | High | Sheeba | Fail | 31.07.23 | 01.08.23
TC_019 | Sortable Columns | Verify the sorting functionality of "Primary Contact" column | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on a column header of "Primary Contact" to sort data | URL: https://www.freshworks.com/ Email ID: test123@gmail.com Domain: Finance | Step1: Should land on the freshworks website dashboard Step2: Products drop-drown should be visible and accessible Step3: Should land on the Freshsales page Step4: Should land on the Signup page and should login successfully Step5: Should land on the Domain page Step6: Should land on the Finance dashboard page Step7: Deal Management drop-down should be visible Step8: Should Land on the Quotes page and existing Quotes should be visible Step9: Primary Contact column in the grid view should be sortable after clicking on the other column as primary contact column has no functionality of sorting action | Step1: Landed on the freshworks website dashboard Step2: Products Drop-down is visible and accessible Step3: Landed on the Freshsales page Step4: Landed on the Signup page and logged in successfully Step5: Landed on the Domain page Step6: Landed on the Finance dashboard page Step7: Deal Management drop-down is visible Step8: Landed on the Quotes page and existing Quotes is visible Step9: Primary Contact column in the grid view is sortable after clicking on the other column as primary contact column has no functionality of sorting action | Medium | Medium | Sheeba | Pass | 31.07.23 | 01.08.23

## Test excution details
User Story 002
Test case number | Test case name | Description | Screenshot
TC_001 | First time user- Quotes Tab with My Quotes | Verify the presence of the Quotes tab with My Quotes and accessing the tool tip
TC_002 | First time user- Quotes Tab with My Quotes | Verify the presence of the Quotes tab with My Quotes and accessing the tool tip
TC_003 | Regular user-Quotes Tab with My Quotes | Verify the presence of the Quotes tab with My Quotes and accessing without the tool tip
TC_005 | View Existing Quotes | Verify the visibility of existing Quotes
TC_007 | Select Multiple Quotes Together | Verify the ability to select multiple Quotes simultaneously
TC_008 | Select Multiple Quotes Together | Verify the ability to select multiple Quotes one by one
TC_010 | Edit Account on the Grid | Verify the visibility of the "Edit Account" option on the grid view of "Quote name" column
TC_012 | Edit Account on the Grid | Verify the visibility of the "Edit Account" option on the grid view of "Primary Contact" column
TC_013 | Edit Account on the Grid | Verify the visibility of the "Edit Account" option on the grid view of "Quote Stage" column
TC_014 | Edit Account on the Grid | Verify the visibility of the "Edit Account" option on the grid view of "Created at" column
TC_015 | Sortable Columns | Verify the sorting functionality of "Quote Name" column
TC_016 | Sortable Columns | Verify the sorting functionality of "Quote Stage" column
TC_017 | Sortable Columns | Verify the sorting functionality of "Created at" column

## Defects
Defect number | Project Name | Module Name | Requirement Number | Test Case ID | Summary | Description | Issues | Severity | Priority | Assign to
DF_001 | Freshworks | Finance | R002 | TC_004 | Quotes Tab with My Quotes | Steps to reproduce: Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down | The Dashboard displayed Quotes Tab without the option "My Quotes" | Low | Medium | Sheeba
DF_002 | Freshworks | Finance | R002 | TC_006 | View Existing Quotes | Steps to reproduce: Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down | The existing Quotes is not visible on the page | High | High | Sheeba
DF_003 | Freshworks | Finance | R002 | TC_009 | Select Multiple Quotes Together | Steps to reproduce: Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Select the multiple quotes one by one using checkboxes | Not able to select multiple quotes one by one using checkboxes | Medium | High | Sheeba
DF_004 | Freshworks | Finance | R002 | TC_011 | Edit Account on the Grid | Steps to reproduce: Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on the edit option of each quotes present on the grid view | The "Edit Account" option is visible but not accessible on the grid view for each Quote of "Quote name" column | High | High | Sheeba
DF_005 | Freshworks | Finance | R002 | TC_018 | Sortable Columns | Step1: Launch the website url Step2: Go to products dropdown Step3: Select Freshsales option Step4: Click on "Start free trial" button Step5: Sign up with your Gmail Account Step6: Select Domain Step7: Locate and point out on the icon of Deal Management dropdown Step8: Choose Quotes option from the drop down Step9: Click on a column header of "Created at" to sort data | "Created at" column in the grid view is sortable and after clicking it is not sorting the data in ascending or descending order | Medium | High | Sheeba

## Defect_Snapshots
User Story 002
Defect number | Issues | Screenshot
DF_001 | The Dashboard displayed Quotes Tab without the option "My Quotes"
DF_002 | The existing Quotes is not visible on the page
DF_003 | Not able to select multiple quotes one by one using checkboxes
DF_004 | The "Edit Account" option is visible but not accessible on the grid view for each Quote of "Quote name" column
DF_005 | "Created at" column in the grid view is sortable and after clicking it is not sorting the data in ascending or descending order

## Story_Point_Effort_and_Reason
Project Name :- | Freshworks
Story Point :- | 1
Reason for story point :- | To verify the feature visibility and accessibility of each functionality
Efforts(in hours) :- | 8 hrs
Reason for Efforts :- | 2-Creation of test cases 2-Execution of test cases 2-Defect/Bug raising 1-Re-testing 1-Documentation

## Test report
SNO | PASS | FAIL | BLOCKERS | NOT EXECUTED | TOTAL TEST CASE | PASS RATIO (%) | TEST IN PROGRESS | DEV IN PROGRESS | DONE | TOTAL DEFECT
2 | 14 | 5 | 0 | 0 | 19 | 73.68% | 0 | 0 | Y | 5